## Sheet1
TASK NAME | START DATE | END DATE
Overall program design and demonstration | 2020-01-01 | 2020-04-01
Design and demonstration of backscattering sensor network platform | 2020-04-01 | 2020-06-01
Design of backscattering sensor network platform | 2020-06-01 | 2020-08-01
Development and measurement of backscattering sensor network platform | 2020-08-01 | 2020-10-01
Development and test of backscattering sensor sensor unit | 2020-10-01 | 2020-12-01
Design and demonstration of moving edge computing scheme | 2020-12-01 | 2021-02-01
Algorithm design | 2021-02-01 | 2021-04-01
Code implementation and modulation | 2021-04-01 | 2021-06-01
Discusses algorithms and optimization code | 2021-06-01 | 2021-08-01
Edge computing and communication scheme design and demonstration | 2021-08-01 | 2021-10-01
Edge learning algorithm design | 2021-10-01 | 2021-12-01
Communication algorithm design | 2021-12-01 | 2022-02-01
Code implementation and modulation | 2022-02-01 | 2022-04-01
Discusses algorithms and optimization code | 2022-04-01 | 2022-06-01
System integration test | 2022-06-01 | 2022-08-01
The measured | 2022-08-01 | 2022-11-01
Topic summary and conclusion | 2022-11-01 | 2022-12-31